## Sheet1
|  | Estimated (h) | Actual (h) | Precedent | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50
Preston
A | Establish Requirements | 7 | 5
B | Create basic prototype | 3 | 5 | A
C | Develop character interactions | 40 | 14 | B
D | Documentation | 6 | 3 | A
E | Animation design | 12 |  | B,C
F | Visual design | 7 | 4 | B
G | Unit testing | 7 |  | B,C
H | System testing | 3 |  | B,C,E
| Total | 85 | 31
Karb
A | Establish Requirements | 5 | 4
B | Group meet & object assignning | 5 | 3 | A
C | Assigned object preview for Karb | 5 | 5 | B
D | Documentation/SA demo | 5 | 4 | B
E | Game demo for Karb | 5 | 7 | C
F | Group meeting | 5 | 1 | C
G | Assigned object preview for Baoying | 5 | 1 | F
H | Game demo for Baoying | 5 | 1 | F
I | Group meeting | 5 |  | H
J | Assigned object preview for the group | 8 |  | I
K | Game demo for release | 8 |  | I
L | Game Engine: set objects for level and set player | 10 | 4 | B
M | Game Model: get objects and draw it | 5 | 2 | B
N | Paint class tool: help paint and control animation | 5 | 4 | B
P | Background: test it and conform, to be used by other classes such as enemies and hero | 5 | 3 | B
| Total | 85 | 39
Dustin
A | Create Demo button ad window | 5 | 12
B | Allow scripting | 2 |  | A
C | Create win script for level one | 2 |  | B
D | Create loose script for level one | 1 |  | C
E | Create win and loose scripts for other level | 4 |  | D
F | Add sound | 3 |  | E
| Total | 17 | 12
Baoying
A | Establish requirements | 5 | 4
B | Group meet & aggign work | 5 | 4 | A
C | Documentation/SA demo | 5 | 4 | B
D | Create prototype | 5 | 5 | B
E | Implement creat new player | 5 | 6 | D
F | Implement load player | 5 | 5 | E
G | Implement help menu | 4 |  | F
H | Implement score | 4 |  | G
I | Implement save score | 4 |  | H
J | Implement logout | 4 |  | I
K | Unit testing | 4 |  | D, E, F, J, H, K
| Total | 50 | 28
Issac
A | Establish Requirements | 5 | 4
B | Team meeting | 5 | 2 | A
C | Add collectibles | 5 | 2 | B
D | Test prototype | 2 |  | C
E | Projectile detection | 6 |  | C
F | Hit detection | 8 |  | E
G | Update player/enemy | 2 |  | F
H | Full build test | 1 |  | G
| Total | 50 | 8
| Group total | 287 | 118
Red: Need to do
Blue: Scheduled for next week
Yellow: Done this week
Green: Completed previously