## Sheet1
|  | Estimated (h) | Actual (h) | Precedent | 5 | 10 | 15 |  | 20 | 25 | 30 | 35 | 40 | 45 | 50
| Preston | [6 empty] | This Week: Finish Up Character Interactions and Testing
A | Establish Requirements | 7 | 5
B | Create basic prototype | 3 | 5 | A
C | Develop character interactions | 40 | 14 | B
D | Documentation | 6 | 3 | A
E | Animation design | 12 |  | B,C
F | Visual design | 7 | 4 | B
G | Unit testing | 7 |  | B,C
H | System testing | 3 |  | B,C,E
| Total | 85 | 31
Karb
A | Establish Requirements | 5 | 4
B | Group meet & object assignning | 5 | 3 | A
C | Assigned object preview for Karb | 5 | 5 | B
D | Documentation/SA demo | 5 | 4 | B
E | Game demo for Karb | 5 | 7 | C
F | Group meeting | 5 | 1 | C
G | Assigned object preview for Baoying | 5 | 1 | F
H | Game demo for Baoying | 5 | 1 | F
I | Group meeting | 5 |  | H
J | Assigned object preview for the group | 8 |  | I
K | Game demo for release | 8 |  | I
L | Game Engine: set objects for level and set player | 10 | 4 | B
M | Game Model: get objects and draw it | 5 | 2 | B
N | Paint class tool: help paint and control animation | 5 | 4 | B
P | Background: test it and conform, to be used by other classes such as enemies and hero | 5 | 3 | B
| Total | 85 | 39
Dustin
A | Create Demo option and window | 5 | 9
B | Get slot call to work on UI window | 12 | 20 | A
C | Create win script for levels | 4 | 4 | B
D | Create loose script for levels | 4 | 4 | C
E | Add level system and levels | 5 | 5 | D
F | Add the option to randomly generate levels | 13 | 8
| Total | 43 | 50
Baoying
A | Establish requirements | 5 | 4
B | Group meet & aggign work | 5 | 4 | A
C | Documentation/SA demo | 5 | 4 | B
D | Create prototype | 5 | 5 | B
E | Implement player | 5 | 2 | D
F | Implement creat new player | 5 | 6 | E
G | Implement load player | 5 | 5 | F
H | Implement help and manual menu | 4 | 3 | G
I | Implement score | 4 |  | H
J | Unit testing | 4 | 3 | E, F, G, H
| Total | 50 | 32
Issac
A | Establish Requirements | 5 | 4
B | Team meeting | 5 | 2 | A
C | Game Base Code | 12 | 8 | B
D | Add collectibles | 5 | 2 | C
E | Test prototype | 2 |  | D
F | Projectile detection | 6 |  | D
G | Hit detection | 8 |  | E, F
H | Update player/enemy | 2 |  | G
I | Full build test | 1 |  | H
| Total | 50 | 16
| Group total | 287 | 138
| Total Estimated Cost & Actual Cost | 28700 | 13800
Red: Need to do
Blue: Scheduled for next week
Yellow: Done this week
Green: Completed previously